## Office of the MM
ORGANISATIONAL SCORECARD FOR 2020/2021
OFFICE OF THE MUNICIPAL MANAGER
MID TERM PERFORMANCE REPORT
INDICATORS |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | ANNUAL TARGET | QUARTER 1 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | QUARTER 2 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | MIDTERM |  |  | QUARTER 3 | QUARTER 4 | BUDGET | WARD INFORMATION | Means of Verification (POE) | RESPONSIBLE DEPARTMENT | REFERNCE
|  |  | IDP REF NO. | MSCOA REF NO | B2B REF N0. |  |  |  |  | 2019/2020 | 2020/2021 | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL | ACHIEVED / NOT ACHIEVED | TARGET | TARGET
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT6 | N/A | B2B-5 | To ensure a functional organisational structure | Review of the municipal orgarnogram | Date of adopted reviewed organogram | 30 June Annually | 2020-06-25 | 2021-06-24 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | N/A | 2021-06-24 | N/A | Institutional | Copy of Organisational structure and Council resolution | Municipal Manager
|  |  | MTD4 | N/A | B2B-5 | To transform the municipality into a performance driven institution | Signing of annual performance agreements for Senior Managers | Number of Performance Agreements Signed | 5 | 5 | 5 | 5 | 5 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 5 | 5 | Achieved | N/A | N/A | N/A | Institutional | Copy of signed agreement | Municipal Manager
|  |  | MIDT8 | N/A | B2B-5 | To ensure that services provided to the municipality by the service providers is of high quality | Assess and Report on Service Providers Performance | Number of Bi-annual Reports Presented on the assessment of service providers | 2 | 4 | 2 | 1 | 1 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | Achieved | 1 | N/A | N/A | Institutional | Reports on Service provider performance | Municipal Manager | \
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN3-4 | N/A | B2B_4 | To ensure effective and efficient supply chain management system | Appointment of Bid Committees (BSC, BEC and BAC) in line with Municipal SCM Policy and regulations. | Date of appointment of all Bid Committees | 31 July annually | New | 2020-07-31 | 2020-07-31 | 2020-07-03 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 2020-07-31 | 2020-07-03 | Achieved | N/A | N/A | N/A | Institutional | Schedule of Bid Committee members and copy of appointment letters signed by the Municipal Manager with acceptance by members | Municipal Manager
|  |  | FIN4-1 | N/A | B2B_4 | To ensure effective and efficient supply chain management system | AFSs submitted to AG by 31 August 2020 | Submission of AFS to Auditor General | 31 August annually | 2019-08-31 | 2020-08-31 | 2020-08-31 | 2020-10-30 | Not Achieved | The NT issued extension for submission of AFS to AG to 31 Oct 2020 due to COVID19 | Submission of AFS to AGSA by 31 October 2020 | N/A | N/A | Not for the period under review | N/A | N/A | 2020-08-31 | 2020-10-30 | Not Achieved | N/A | N/A | N/A | Institutional | AFS and proof of receipt from the Office of the Auditor General | Municipal Manager
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1-1 | N/A | B2B_3 | To implement and maintain effective enterprise risk management system | Finalise Risk Management Workshop | No of Bi-Annual risk management Workshops Conducted | 2 | 2 | 2 | 1 | 1 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | Achieved | N/A | 1 | N/A | Institutional | Risk register and workshop registers | Municipal Manager
|  |  | GG1-2 | N/A | B2B_3 |  | Review and adopt the Risk Management Strategy and Policy | Date of the Strategy and Policy adoption by Council | 30 June Annually | 2020-06-30 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-06-30 | N/A | Institutional | Reviewed risk management strategy & Policy and Council resolution | Municipal Manager
|  |  | GG1-3 | N/A | B2B_3 |  | Functional Risk Management through risk committee meetings | Number of quarterly risk management meetings held | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Updated risk register, minutes and attendance register | Municipal Manager
|  |  | GG2-1 | EXP - FIN | B2B_3 | To provide reasonable assurance on the adequacy and effectiveness of internal control system | Prepare and approve the internal audit plan | Date Internal Audit Plan approved by Audit Committee | 30 June Annually | 2020-06-30 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-06-30 | 1100000 | Institutional | Audit Plan and Audit Committee Resolution | Municipal Manager
|  |  | GG2-2 | N/A | B2B_3 |  | Implementation of the Internal Audit Plan | Number of Internal Audit Progress Reports produced and submitted to the MM and Audit Committee | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Reports, audit committee minutes, register and acknowledgment by MM | Municipal Manager
|  |  | GG2-3 | N/A | B2B_3 |  | Review and submit audit charter to the audit committee for approval | Date of approval of the Internal Audit Charter by Audit Committee | 30 June Annually | 2020-06-30 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-06-30 | N/A | Institutional | Copy of Audit charter and audit committee minutes and register | Municipal Manager
|  |  | GG2-4 | N/A | B2B_3 |  | Review and submit the Performance and Audit Committee charter | Date of approval and adoption of the Performance and Audit Committee charter by Council | 30 June Annually | 2020-06-30 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-06-30 | N/A | Institutional | Council resolution and copy of audit charter | Municipal Manager
|  |  | GG3-1 | N/A | B2B_3 | To ensure and effective Audit and Performance Committee | Coordinate and hold the Audit Committee Meetings | Number of quarterly Audit Committee Meetings Held | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Minutes and attendance registers | Municipal Manager
|  |  | GG3-2 | N/A | B2B_3 |  | Coordinate and hold performance Audit Committee Meetings | Number Performance Audit Committee Meetings Held | 2 | 2 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | 1 | N/A | Institutional | Minutes and attendance registers | Municipal Manager
|  |  | GG4-1 | N/A | B2B_3 | To transform the municipality into a performance driven institution | Quarterly Performance Reports on achieved and not achieved targets submitted to Council | Number of quartely Performance Reports Submitted to Council | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Quarterly PMS Report and Council resolution | Municipal Manager
|  |  | GG4-3 | N/A | B2B_3 |  | Conduct performance appraisals for section 56/57 | Number of Section 56/57 employees appraisals conducted | 1 | 1 | 1 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 1 | N/A | N/A | Institutional | Performance Agreements and Council Resolutions | Municipal Manager
|  |  | GG4-4 | N/A | B2B_3 |  | To ensure that the mid-year Performance Report is prepared and submitted | Date of submission of Mid Year Performance report to Council, Provincial and National Treasury | 25 January Annually | 2020-01-25 | 2021-01-25 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 2021-01-25 | N/A | N/A | Institutional | Mid Year performance report and proof of submission | Municipal Manager
|  |  | GG4-5 | N/A | B2B_3 |  | To ensure that the mid -year Budget Report is prepared and submitted | Date of submission of mid-year budget report to Council, Provincial and National Treasury | 25 January Annually | 2020-01-25 | 2021-01-25 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 2021-01-25 | N/A | N/A | Institutional | Report and proof of submission | Municipal Manager
|  |  | GG4-6 | N/A | B2B_3 |  | To prepare and table the draft Annual report to Council | Date annual report tabled to Council | 31 January Annually | 2020-01-25 | 2021-01-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 2021-01-31 | N/A | N/A | Institutional | Draft AR and Council Resolution | Municipal Manager
|  |  | GG4-7 | N/A | B2B_3 |  | Coordinate the Oversight committee meeting to consider the adoption of the annual report | Date of Oversight Committee (MPAC) Meeting | 31 March Annually | 2020-03-31 | 2021-03-23 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 2021-03-23 | N/A | N/A | Institutional | Oversight report and Minutes | Municipal Manager
|  |  | GG4-8 | N/A | B2B_3 |  | To facilitate the Oversight Process and table a report to Council for Adoption | Date of Oversight report adopted by council | 31 March Annually | 2020-03-31 | 2021-03-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 2021-03-31 | N/A | N/A | Institutional | Council resolution | Municipal Manager
|  |  | GG4-9 | N/A | B2B_3 |  | To finalise and adopt Annual Report | Date of Annual Report adoption by Council | 31 March Annually | 2020-03-31 | 2021-03-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | 2021-03-31 | N/A | N/A | Institutional | Council resolution | Municipal Manager
|  |  | GG5 | N/A | B2B_3 | Ensure Functional Public Municipal Accounts Committee | Coordinate Municipal Public Accounts Committee meetings | Number of quarterly Municipal Public Accounts Committee Meetings Held | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Minutes | Municipal Manager
|  |  | GG10-1 | N/A | B2B_3 | To ensure continous engagement with ward constituencies | To coordinate Monthly Ward Committee meetings in 7 wards | Number of ward committee meetings held per Quarter | 84 | 84 | 84 | 21 | Not Achieved - only 8 Ward committee meetings were held out of 21 | Not Achieved | Meetings were not held due to the National Lockdown | Meetings will resume in Q2 | 21 | 18 | Not Achieved | All meetings were held in all wards, not all minutes and regsiters were submitted | Submission of registers and minutes will be discussed with the ward committees | 42 | 26 | Not Achieved | 21 | 21 | N/A | Ward1,2,3,4,5,6,7 | Minutes and attendance Registers | Municipal Manager
|  |  | GG 10-2 | N/A | BSB _3 | To ensure contoius engagement with the Communities in all 7wards | To hold Public Meetings | Number of Public Meetings held per Quarter | 28 | New | 28 | 7 | Not Achieved - no public meetings were held | Not Achieved | Meetings were not held due to the National Lockdown | Meetings will resume in Q2 | 7 | 12 | Achieved | N/A | N/A | 14 | 12 | Not Achieved | 7 | 7 | N/A | Ward 1-7 | Minutes & Attendance Registers | Municipal Manager
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC1-1 | N/A | B2B_2 | To ensure strategic development and management of the municipality’s Integrated Development Plan | Development and approval of the IDP/ Budget Process Plan | Date of adoption of the 2021/2022 IDP/ Budget Process Plan | 2020-08-31 | 8/25/20219 | 2020-08-31 | 2020-08-31 | 2020-08-27 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 2020-08-31 | 2020-08-27 | Achieved | N/A | N/A | N/A | Institutional | Process plan and Council Resolution | Municipal Manager
|  |  | CC1-2 | N/A | B2B_2 |  | Co odinate the IDP Representative Forum meetings | Number of Bi- Annual IDP Representative Forum meetings co ordinated | 2 | 2 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | 1 | N/A | Institutional | Attendance registers and/or minutes | Municipal Manager
|  |  | CC1-3 | N/A | B2B_2 |  | Adoption and Implementation of the Integrated Development Plan (IDP) focusing on delivery of 10 critical municipal services | Date of adoption of the 2021/2022 IDP | 2020-06-30 | 2020-06-30 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | IDP Draft review in progress | Submitted IDP input to IDP Officer | Achieved | N/A | N/A | IDP Draft review in progress | Submitted IDP input to IDP Officer | Achieved | N/A | 30 June 2021 (Final adoption) | N/A | Institutional | IDP, report and Council resolution | Municipal Manager

## Corporate Services
ORGANISATIONAL SCORECARD FOR 2020/2021
CORPORATE SERVICES
MID TERM PRFORMANCE REPORT
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | ANNUAL TARGET | QUARTER 1 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | QUARTER 2 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | MIDTERM |  |  | QUARTER 3 | QUARTER 4 | BUDGET | WARD INFORMATION | Means of Verification (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | MSCOA REF NO | B2B REF N0. |  |  |  |  | 2019/2020 | 2020/2021 | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL | ACHIEVED / NOT ACHIEVED | TARGET | TARGET
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT1 | N/A | B2B_5 | To ensure that municipal staff and councillors are informed | Development of Gifts & Rewards Policy | Date of submission of the policy to MANCO, LLF & Council | Annually | New | 2021-04-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Submit policy to MANCO by 31 December 2020 | Not Achieved - Policy was not submitted to MANCO | Not Achieved | The process of reviewing the policy is on going and had not been finalised at by 31 December 2020 as it needed to be submitted to LLF before Council. | The policy will be submitted to Council by 31 June 2021 | Submit policy to MANCO by 31 December 2020 | Not Achieved - Policy was not submitted to MANCO | Not Achieved | Submit policy to LLF by 31 March 2021 | submit policy to Council for approval by 30 April 2021 | N/A | Institutional | Q2 MANCO Minutes & attendance register, Q3 LLF Minutes & attendance register & Q4 Council Resolution | Corporate Services
|  |  | MIDT1- 2 | N/A | B2B_5 |  | Review of the Retention Policy | Date of Reviewed Retention Policy tabled to Council for approval | Annually | New | 2020-09-30 | 2020-09-30 | Draft Retention policy | Not Achieved | This policy is work in progress due to Covid delays. | The policy will be sent to Council for approval by 31 January 2021 | N/A | N/A | Not for the period under review | N/A | N/A | 2020-09-30 | Draft Retention policy | Not Achieved | N/A | N/A | N/A | Institutional | Council resolution and Retention policy | Corporate Services
|  |  | MIDT1-3 | N/A | B2B_5 |  | Review of the Internal Busary Policy | Date of review approval by Council | Annually | New | 2020-12-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | Not Achieved - Review of the Internal Bursary Policy was not sent to council | Not Achieved | The process of reviewing the policy is on going and had not been finalised at by 31 December 2020 as it needed to be submitted to LLF before Council. | The policy will be submitted to Council by 31 June 2021 | 2020-12-31 | Not Achieved - Review of the Internal Bursary Policy was not sent to council | Not Achieved | N/A | N/A | N/A | Institutional | Council resolution and Internal Bursary policy | Corporate Services
|  |  | MIDT2-1 | N/A | B2B_5 | To ensure that municipal staff is skilled according to job requirements | Development and submission of Workplace Skilled Plan | Date of WSP developed, tabled to LLF and Council and submitted to LGSETA | 30 April- Annually | 2020-04-30 | 2021-04-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | Submit WSP inputs to LLF | Submit WSP and Council resolution to LGSETA by 2021/04/30 | N/A | Institutional | Q2 screenshot of WSP WIP, Q3 LLF Minutes & attendance register, Q4 Council Resolution and LGSETA Receipt Confirmation letter | Corporate Services
|  |  | MIDT2-2 | N/A | B2B_5 |  | Implementation of the WSP | Number of quarterly WSP progress reports submitted to portfolio committee | 4 | New | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Report, portfolio minutes and attendance register | Corporate Services
|  |  | MTD4 | N/A | B2B-5 | To transform the municipality into a performance driven institution | Signing of annual performance agreements for Senior Managers | Number of Performance Agreements Signed | 1 | 1 | 1 | 1 | 1 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | N/A | Institutional | Copy of signed agreements | Corporate Services
|  |  | MIDT5 | N/A | B2B-5 | To promote occupational health and safety in the work place | Health and Safety Committee | Number of quarterly Health and Safety Committee Meetings | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | OHS Committee Minutes and attendance registers | Corporate Services
|  |  | MIDT7 | N/A | B2B-5 | To ensure that efficient and effective fleet management | Fleet management reports to portfolio committee | Number of reports submitted to portfolio committee | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Fleet management reports, portfolio minutes and attendance registers | Corporate Services
|  |  | MIDT7-1 | N/A | B2B-5 |  | Review of the Municipal Fleet Policy | Date of review approval by Council | Annually | new | 2020-12-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | Fleet policy not tabled to Council for approval | Not Achieved | Policy development was delayed by the absence of the fleet officer as well as departure of the Director. | This will be concluded by 30 June 2021 as the new Director has started. | 2020-12-31 | Fleet policy not tabled to Council for approval | Not Achieved | N/A | N/A | N/A | Institutional | Council resolution and Fleet policy | Corporate Services
|  |  | MIDT8 | N/A | B2B-5 | To ensure that services provided to the municipality by the service providers is of high quality | Assess and Report on Service Providers Performance | Number of Bi-annual Reports Presented to Municipal Manager on the assessment of service providers | 2 | 4 | 2 | 1 | 1 | Achieved | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | Achieved | 1 | N/A | N/A | Institutional | Reports on Service provider performance | Corporate Services
|  |  | MIDT9 | GG026 | B2B-5 | To ensure effective and efficient ICT Management | Development and approval of the Municipality's ICT Disaster Recovery Plan | Date of ICT Disaster Recovery Plan approval | Review as and when required | New | 2021-04-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Appoint Service Provider | Appointment of service providers | Achieved | N/A | N/A | Appoint Service Provider | Appointment of service providers | Achieved | Preliminary Report Submission by Service Provider to ICT Steering Committee | Submission of Disaster Recovery Plan to Council for adoption by 30 April 2021 | 200000 | Institutional | Q2 Appointment Letter,Q3 ICT Steering Committee Minutes & attendance register, Q4 Council Resolution | Corporate Services
|  |  | MIDT9-1 | N/A | B2B-5 | To promote healthy lifestyle amongst employees | To co ordinate 2 wellness programmes | Dates for implementaion of Wellness programmes | Bi-Annual | New | 31-Dec-20 and 30-Jun-21 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | 2020-12-11 | Achieved | N/A | N/A | 2020-12-31 | 2020-12-11 | Achieved | N/A | 2021-06-30 | N/A | Institutional | Attendance registers | Corporate Services
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN1 | N/A | B2B_4 | To Ensure efficient and effective budget management | To monitor ICT third party costs on quarterly basis | Number of quarterly reports submitted to Community & Corporate Services Portfolio on ICT third party costs | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Reports to the portfolio, Minutes and Portfolio attendance registers | Corporate Services
|  |  | FIN3 | N/A | B2B_4 | To ensure effective and efficient supply chain management system | Develop the Departmental Procurement Plan to ensure timous procurement of required goods and services | Date of Submission of procurement plan inputs to Finance | 30 April Annually | New | 2021-04-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | 2021-04-30 | N/A | Institutional | Acknowledgement from finance, Procurement Plan | Corporate Services
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1-3 | N/A | B2B_3 | To implement and maintain effective enterprise risk management system | Functional Risk Management through risk committee meetings | Number of quarterly risk management meetings held | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Quarterly Risk Submission register and minutes | Corporate Services
|  |  | GG4-1 | N/A | B2B_3 | To transform the municipality into a performance driven institution | Quarterly Performance Reports on achieved and not achieved targets submitted to PMS Unit | Number of quartely Performance Reports Submitted to PMS Unit | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Quarterly PMS Report and Submission register | Corporate Services
|  |  | GG11-1 | N/A | B2B_3 | To improve functioning of the municipality through oversight committees functionality | Coordinate Meetings of Local labour Forum | Number of meetings held | 4 | 4 | 4 | 1 | 1 | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | LLF Minutes and Attendance Registers | Corporate Services
|  |  | GG11-2 | N/A | B2B_3 |  | Coordinate Meetings of EXCO | Number of meetings held | 11 | 11 | 11 | 3 | 2 | Not Achieved | Due to the lockdown in July the EXCO did not convene as scheduled | Meetings will resume as per council calendar after the lockdown regulations and levels have been lifted | 2 | 2 | Achieved | N/A | N/A | 5 | 4 | Not Achieved | 3 | 3 | N/A | Institutional | Minutes and Attendance registers | Corporate Services
|  |  | GG11-3 | N/A | B2B_3 |  | Coordinate Meetings of Council | Number of meetings held | 11 | 11 | 11 | 3 | 3 | Achieved | N/A | N/A | 2 | 2 | Achieved | N/A | N/A | 5 | 5 | Achieved | 3 | 3 | N/A | Institutional | Minutes and Attendance registers | Corporate Services
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC1-2 | N/A | B2B_2 | To ensure strategic development and management of the municipality’s Integrated Development Plan | Corodinate the IDP Representative Forum meetings | Number of Bi- Annual IDP Representative Forum meetings co ordinated | 2 | 2 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | 1 | N/A | Institutional | Attendance registers and/or minutes | Corporate Services

## Finance Dept
ORGANISATIONAL SCORECARD FOR 2020/2021
FINANCIAL SERVICES DEPARTMENT
MID TERM PERFORMANCE REPORT
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | ANNUAL TARGET | QUARTER 1 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | QUARTER 2 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | MIDTERM |  |  | QUARTER 3 | QUARTER 4 | BUDGET | WARD INFORMATION | Means of Verification (POE) | RESPONSIBLE DEPARTMENT | REFERENCE
|  |  | IDP REF NO. | MSCOA REF NO | B2B REF N0. |  |  |  |  | 2019/2020 | 2020/2021 | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL | ACHIEVED / NOT ACHIEVED | TARGET | TARGET
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT8 | N/A | B2B-5 | To ensure that services provided to the Municipality by service providers is of high quality | Assess and Report on Service Providers Performance | Number of Bi-annual Reports Presented on the assessment of service providers | 2 | 4 | 2 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | ACHIEVED | 1 | N/A | N/A | Institutional | Reports on Service provider performance | Chief Financial Officer
|  |  | MTD4 | N/A | B2B_5 | To transform the municipality into a performance driven institution | Signing of annual performance agreements for Senior Managers | Number of Performance Agreements Signed | 4 | 4 | 1 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Performance Agreement | Chief Financial Officer
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT | OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME | OUTCOME 4: DECENT EMPLOYMENT THROUGH INCLUSIVE GROWTH | LED8 | N/A | B2B-1 | To Promote emerging Businesses | Increase number of Award made to BBBEE level 1 emerging businesses for bids more than R30 000. | Number of SCM reports on bids awarded to BBBEE Level 1 emerging business | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Ward 1,2,3,4,5,6,7 | SCHEDULE OF AWARDS, COPY OF PURCHASE ORDER/ APPOINTMENT LETTER AND BBBEE CERTIFICATE | Chief Financial Officer
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN2 | N/A | B2B_4 | To improve reporting Management | Preparation of quartely report to Council (section 52d of MFMA) | Number of Section 52 D reports submitted to Council | 4 | 0 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Institutional | Section 52 (d) report and Council resolution | Chief Financial Officer
|  |  | FIN3-1 | N/A | B2B_4 | To ensure effective and efficient supply chain management system | Develop Procurement Plan to ensure timous procurement of required goods and services | Date of procurement plan submitted to Portfolio Committee and Council | 2020-05-31 | 2020-05-31 | 2021-05-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-05-31 | N/A | Institutional | Procurement plan, Portfolio minutes and Council resolution | Chief Financial Officer
|  |  | FIN3-2 | N/A | B2B_4 |  | Convening of BEC within 15 days after the closing date of an advert | Number/Cycle of days of BEC meetings held after closing date of an advert | 15 days | 15 days | 15 days | 15 days | Not achieved project 1 took 27 days, project 2 took 25 days and project 3 took 47 days | NOT ACCHIEVED | Of the 4 projects only 1 was achieved according to the number od days, the other 3 projects that took more that 15 days the problem was addressed | A meeting schedule will be developed by Q2 to ensure BEC Meetings convene within 15 days after the closing date of an adver | 15 days | BEC meetings Not achieved | NOT ACCHIEVED | 4 project was took more that 15 days and we did try to address this problem | Proposed table for meetings will be compiled by Q2 30 March 2021 | 15 days | BEC meetings Not achieved | NOT ACCHIEVED | 15 days | 15 days | N/A | Institutional | BID minutes and attendance register | Chief Financial Officer
|  |  | FIN3-3 | N/A | B2B_4 |  | Convening of BAC within 14 working days after the BEC meetings | Number/Cycle of days of BAC meetings held after the BEC processes | 14 days | 14 days | 14 days | 14 days | Out of the 4 projects 3 were Not achieved, project 1 took 27 days, project 2 took 27 days and project 3 took 43 days | ACHIEVED | N/A | N/A | 14 days | 14 Days | ACHIEVED | N/A | N/A | 14 days | 14 Days | ACHIEVED | 14 days | 14 days | N/A | Institutional | BID minutes and attendance register | Chief Financial Officer
|  |  | FIN4-1 | N/A | B2B_4 | To ensure compilation of a credible Annual Financial Statements | AFSs submitted to AG by 31 August 2020 | Submission of AFS to Auditor General | 2019-08-31 | 2019-08-31 | 2020-08-31 | 2020-08-31 | AFS submitted submitted on the 31 October 2020 - Not achieved | NOT ACCHIEVED | The NT issued extension for submission of AFS to AG to 31 Oct 2020 due to COVID19 | Submission of AFS to AGSA by 31 October 2020 | N/A | N/A | ACHIEVED | N/A | N/A | N/A | N/A | ACHIEVED | N/A | N/A | N/A | Institutional | AFS and proof of receipt from the Office of the Auditor General | Chief Financial Officer
|  |  | FIN4-2 | N/A | B2B_4 |  | Monitor the preparation of Annual Financial Statements to ensure crediblity | Municipal Manager to ensure that the Municpality Receives unqualified report | 2020-12-31 | 2020-12-31 | 2020-12-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | AG report not received target Not achieved | NOT ACCHIEVED | AG is currently on site and auditing the AFS | Report will be submiited by 28 February 2021 | 2020-12-31 | AG report not received target Not achieved | NOT ACCHIEVED | N/A | N/A | N/A | Institutional | Auditor Generals Reports | Chief Financial Officer
|  |  | FIN5 | N/A | B2B_4 | To ensure effective and efficient asset management | Fixed Asset Register reconciliation performed and signed off by the Chief Financial Officer | Number of Monthly reports on Fixed Asset Register reconciliation | 12 | 12 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Reports signed by the Chief Financial Officer | Chief Financial Officer
|  |  | FIN6-1 | N/A | B2B_4 | To ensure revenue enhancement | Development and approval of a revenue enhancement strategy | Date of revenue enhancement approval | 2020-06-30 | New | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Stategy process preparation | Draft Stratergy | ACHIEVED | N/A | N/A | Stategy process preparation | Draft Stratergy | ACHIEVED | Stategy process preparation | 2021-06-30 | N/A | Institutional | Finance system generated reports and correspondance from the billing office, Revenue Stratergy approved/ Council Resolution | Chief Financial Officer
|  |  | FIN6-2 | N/A | B2B_4 |  | Quarterly age analysis reports prepared and submitted to Council | Quaterly Age analysis reports submitted to Council | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Institutional | Reports and council resolution | Chief Financial Officer
|  |  | FIN6-3 | N/A | B2B_4 |  | Increased percentage of debts collection rate | Percentage of debts Collection: Amount collected | 70% | 70% | 70% | 70% | 90% | ACHIEVED | N/A | N/A | 70% | 112% | ACHIEVED | N/A | N/A | 70% | 112% | ACHIEVED | 70% | 70% | N/A | Institutional | Reports | Chief Financial Officer
|  |  | FIN7 | N/A | B2B_4 | To ensure that the Municipal Liquidity position is managed at 1:10 | prepare quarterly reports on cost coverage ratio Ratio [All available cash at a particular time) + (Investments)- Conditional grants)]/ Monthly fixed operating expenditure) | Cost coverage ratio submitted to Council | 1:10 | 1:10 | 1:10 | 1:10 | 1:10 | ACHIEVED | N/A | N/A | 1:10 | 1:10 | ACHIEVED | N/A | N/A | 1:10 | 1:10 | ACHIEVED | 1:10 | 1:10 | N/A | Institutional | Reports and council resolution | Chief Financial Officer
|  |  | FIN8 | N/A | B2B_4 | To ensure that VAT is accounted for | Prepare monthly Vat Reconciliations | Number of monthly vat Reconciliations prepared and signed by the Chief Financial Officer | 12 | 12 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Reports signed by the Chief Financial Officer | Chief Financial Officer
|  |  | FIN9 | N/A | B2B_4 | To ensure effective management of the payroll system | Prepare and submit monthly Payroll Reconciliation to Senior Management | Number of monthly payroll Reconcilliation reports submitted to senior managers within 7 days after pay day | 12 | 12 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Reports and signed proof of receipt by managers | Chief Financial Officer
|  |  | FIN10-1 | N/A | B2B_4 | To ensure effective and efficient grants management | Prepare and submit monthly Reconciliation of grants income | Number of monthly reports on reconciliations of grants income signed off by the Chief Financial Officer | 12 | 12 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Reports signed by the Chief Financial Officer | Chief Financial Officer
|  |  | FIN10-2a | N/A | B2B_4 |  | Prepare and submit financial reports on EPWP allocation spending | Quaterly reports on % Spent on EPWP allocation submitted to Public Works | 12 | 12 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Report and proof of submission (email correspondance copy) | Chief Financial Officer
|  |  | FIN11 | N/A | MK4 | To improve management and implementation of Capital Budget in the Municipality | % of the capital budget actually spent on capital projects | Quaterly reports on % Spent (Total spending on capital projects / Total capital budget) x 100 on capital projects | 100% | 100% | 100% | 20% | 52% | ACHIEVED | N/A | N/A | 20% |  | ACHIEVED | N/A | N/A | 20% | 52% | ACHIEVED | 35% | 25% | N/A | Institutional | MIG Implementation Plan and proof of payments | Technical Services
|  |  | FIN12-1 | N/A | B2B_4 | To ensure enforcement of sound financial management practices | Submit Reports to the Finance Portfolio Committee on a quartely basis | Number of Finance Committee Report Submitted | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
|  |  | FIN12-2a | N/A | B2B_4 |  | Monitor financial ratios to ensure financial stability | Maintain a favourable Debt coverage Ratio (Total operational revenue less operational grants/ debt service payment due within the financial year) | 2:01 | 1:01 | 2:01 | 2:01 | 2:01 | ACHIEVED | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2:01 | 2:01 | ACHIEVED | 2:01 | N/A | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
|  |  | FIN12-2b | N/A | B2B_4 |  |  | Maintain a favourable for outstanding service debtors to revenue (Total outstanding service debtors divide by annual revenue from services) | 1:01 | 1:01 | 1:01 | 1:01 | 1:01 | ACHIEVED | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1:01 | 1:01 | ACHIEVED | 1:01 | N/A | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
|  |  | FIN12-2c | N/A | B2B_4 |  |  | Maintain a favourable Costs coverage ratio: (available cash less unspent conditional grants-overdraft) plus short term investments) divided (by monthly fixed operating expenditure less depreciation, amortization, prov for bad debts, impairment and loss of disposal of assets) | 1:7 | 1.6 | 1:7 | 1:7 | 1:7 | ACHIEVED | N/A | N/A | 1:7 | 1:7 | ACHIEVED | N/A | N/A | 1:7 | 1:7 | ACHIEVED | 1:7 | 1:7 | N/A | Institutional | Reports and Finance Committee Minutes | Chief Financial Office
|  |  | FIN12-3 | N/A | B2B_4 |  | Prepare and submit monthly Bank Reconciliations signed by the Chief Financial Officer | Number of Monthly bank reconciliation | 12 | 4 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Monthly reconciliations signed by the Chief Financial Officer | Chief Financial Officer
|  |  | FIN12-4 | N/A | B2B_4 |  | Prepare and submit monthly Creditors Reconciliations signed by the Chief Financial Officer | Number of Monthly creditors reconciliation and age analysis | 12 | 4 | 12 | 3 | 3 | ACHIEVED | N/A | N/A | 3 | 3 | ACHIEVED | N/A | N/A | 6 | 6 | ACHIEVED | 3 | 3 | N/A | Institutional | Age analysis and Monthly reconciliations signed by the Chief Financial Officer | Chief Financial Officer
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1-3 | N/A | B2B_3 | To implement and maintain effective enterprise risk management system | Functional Risk Management through risk committee meetings | Number of quarterly risk management meetings held | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Institutional | Risk register and minutes | Chief Financial Officer
|  |  | GG4-1 | N/A | B2B_3 | To transform the municipality into a performance driven institution | Quarterly Performance Reports on achieved and not achieved targets submitted to PMS Unit | Number of quartely Performance Reports Submitted to PMS Unit | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Institutional | Quarterly PMS Report and Submission register | Chief Financial Officer
|  |  | GG12 | N/A | B2B_3 | To provide reasonable assurance on the adequacy and effectiveness of internal control system | Development and management of an audit action plan to maintain a clean audit opinion | Quaterly audit action plan reports submitted to Council | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | N/A | Institutional | Reports and Council Resolution | Chief Financial Officer
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC1-1 | N/A | B2B_2 | To ensure strategic development and management of the municipality’s Integrated Development Plan | Development and approval of the IDP/ Budget Process Plan | Date of adoption of the 2021/2022 IDP/ Budget Process Plan | 2020-08-31 | 8/25/20219 | 2020-08-31 | 2020-08-31 | 2020-08-27 | ACHIEVED | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-08-31 | 2020-08-27 | ACHIEVED | N/A | N/A | N/A | Institutional | Process plan and Council Resolution | Chief Financial Officer
|  |  | CC1-2 | N/A | B2B_2 |  | Corodinate the IDP Representative Forum meetings | Number of IDP Representative Forum meetings | 2 | 2 | 2 | N/A | 2020-08-27 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | 1 | N/A | Institutional | Attendance registers and/or minutes | Chief Financial Officer
|  |  | CC1-3 | N/A | B2B_2 |  | Adoption and Implementation of the Integrated Development Plan (IDP) focusing on delivery of 10 critical municipal services | Date of adoption of the 2021/2022 IDP | 2021-06-30 | 2020-06-30 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | IDP Draft review in progress | Submitted IDP input to IDP Officer | ACHIEVED | N/A | N/A | IDP Draft review in progress | Submitted IDP input to IDP Officer | ACHIEVED | N/A | 2021-06-30 | N/A | Institutional | Plan and Portfolio Minutes | Chief Financial Officer

## Community Services
ORGANISATIONAL SCORECARD FOR 2020/2021
COMMUNITY SERVICES DEPARTMENT
MID TERM PERFORMANCE REPORT
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | ANNUAL TARGET | QUARTER 1 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | QUARTER 2 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | MIDTERM |  |  | QUARTER 3 | QUARTER 4 | BUDGET | WARD INFORMATION | Means of Verification (POE) | RESPONSIBLE DEPARTMENT
|  |  | IDP REF NO. | MSCOA REF NO | B2B REF N0. |  |  |  |  | 2019/2020 | 2020/2021 | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL | ACHIEVED / NOT ACHIEVED | TARGET | TARGET
NKPA: BASIC SERVICE DELIVERY
KEY PERFORMANCE AREA: BASIC SERVICE DELIVERY | OUTPUT 2: IMPROVING ACCESS TO BASIC SERVICES | OUTCOME 6: AN EFFICIENT, COMPETITIVE AND RESPONSIVE ECONOMIC INFRASTRUCTURE NETWORK | BSD4-1a | BS003 | B2B_2 | To ensure a safe and health environment | Establishment of ward-based central waste sorting and disposal areas managed through EPWP and CWP Programmes | Number of Central waste sorting and disposal centreby the end of the financial year in all 7 wards by 30 June 2021 | 7 | New | 7 | 2 (Ward 1 and 3) | 0 | Not Achieved | This project is work in progress. The recycling programme is currently implemented in-house while disposal sites are being identified and set up in all wards. (POE submitted) | The waste sorting spaces for the 2 wards will be sorted by end of Quarter 2. | 2 (Ward 4 and 6) | 1 project achieved in ward 4 | Not Achieved | This project is work in progress. 1 waste sorting centre has been established in ward 4 and ward 6 is work in progress | The waste sorting spaces for ward 6 will be established by Q4 30 June 2021. | 2 (Ward 1 and 3) | 1 project achieved in ward 4 | Not Achieved | 2 (Ward 5 and 2) | 1 (Ward 7) | 600000 | Institutional | Reports to portfolio committee and pictures | Community Services
|  |  | BSD4-2 |  |  |  | Review and adopt the Municipality's Integrated Waste Management Plan | Date of IWMP adoption by Council | 2020-05-31 | New | 2021-05-31 | Set up Coordinating structure | Coordinating structure set up on 2020/09/29 | ACHIEVED | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Set up Coordinating structure | Coordinating structure set up on 2020/09/29 | ACHIEVED | Consolidation and Submission to Portfolio Committee | 2021-05-31 |  | Institutional for all wards | Set up coordinating structure, (Q3) target= Consolidation and Submission to Portfolio Committee (Q4) target = Adopted IWMP and Council Resolution | Community Services
|  |  | BSD4-3 |  | B2B_2 |  | Provide Refuse Removal Services to all households within the town area | Number of households provided with Refuse Removal Service on a monthly basis | Total number of households as per valuation roll | 412 | 396 | 396 | 396 | ACHIEVED | N/A | N/A | 396 | 396 | ACHIEVED | N/A | N/A | 396 | 396 | ACHIEVED | 396 | 396 |  | Ward 3 and 4 | Billing reports | Community Services
|  |  | BSD4-4a | LED 33.1 |  |  | Co-ordinate quartely cleaning and waste management awareness campaigns | Number of cleaning campaigns completed in Camperdown CBD, Midillovo, Eston and Nkanyezini Taxi Rank | 4 | 6 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 2 | ACHIEVED | 1 | 1 | 80000 | Ward 3, 4 and 6 | Pictures and report | Community Services
|  |  | BSD4-4b |  |  |  |  | Number of waste management awareness campaigns done in schools within ward 2, ward 1, ward 5 and ward 7 | 4 | 8 | 4 | 1 | 2 | ACHIEVED | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | 2 | 3 | ACHIEVED | 1 | 1 |  | Ward 1,2,5,7 | Pictures and report | Community Services
|  |  | BSD5-1 | LED 005.2 | B2B_2 | To ensure provision of free Basic Services for indigent residents of Mkhambathini Municipality | Review the indigent register | Date of Indigent Register Review and approval by Council | 31 May Annually | 2020-06-30 | 2021-05-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-05-31 | 430000 | Ward 1,2,3,4,5,6,7 | Indigent register and Council Resolution | Community services
|  |  | BSD5-2 |  |  |  | Provide social relief support to indigent families within all wards | Number of quarterly social relief reports submitted to portfolio committee | 1 | 2 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | Report was not ready to be sent to portfolio committee | Not Achieved | The report was not ready for presentation to portfolio committee as data had to be collated from finance and community services | The report will be submitted in quarter 3. | 1 | Report was not ready to be sent to portfolio committee | Not Achieved | N/A | 1 |  | Institutional | Report on social relief support and Portfolio committee minutes | Community services
|  |  | BSD6 |  |  | To ensure that the municipal infrastructure assests are maintained | Finished infrastructure projects hand over to the community: Names of projects | Date of hand over of all complete infrastructure projects | End of Quarter 4 - annually | New | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Hand over plan development (Incl list of projects) and presented to portfolio committee by the end of Q2 | Hand over paln was not achieved | Not Achieved | Target haas been reviewed | The plan would be submitted to the portfolio committee by Q3 31 March 2021 | Hand over plan development (Incl list of projects) and presented to portfolio committee by the end of Q2 | Hand over paln was not achieved | Not Achieved | N/A | 2021-06-30 | N/A | Institutional | Pictures (Q4) and report to portfolio | Community services
NKPA: MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT3-1 | FV0303 | B2B_5 | Create Job opportunities through Public Employment Programmes | Public Employment Programmes job opportunities created | Number of Jobs Created through Public Employment Programmes: EPWP (Waste Management, Ngezandla zethu, Town Beautification, Sports Stars, Asiphephe, caretakers) Environmental Affairs Green Deeds Programme | 200 per annum | 147 | 150 (Not Accummulative) | 150 | 149 | Not Achieved | 3 participant left due to securing stable jobs | The gaps will be closed as and when there are new participants available | 150 | 129 | Not Achieved | Participants have been dropping out | The gaps will be closed as and when there are new participants available, by Q4 30 June 2021 | 150 | 129 | Not Achieved | 150 | 150 | R1.1m | Ward 1,2,3,4,5,6,7 | EPWP contracts and lists for Good Green Deeds | Community Services
|  |  | MIDT3-2 | N/A |  |  | Implement exit strategies through training and Development | Number of trainings provided | 4 | New | 3 | N/A | N/A | Not applicable in Q1 | N/A | N/A | 1 - Coaching Clinic for Sports Stars | 1 - Coaching Clinic for Sports Stars and sports development | Achieved | N/A | N/A | 1 - Coaching Clinic for Sports Stars | 1 - Coaching Clinic for Sports Stars and sports development | Achieved | 1 - Land Scaping Training for Town Beautification | 1- Recycling/ Waste management Training | N/A | Ward 1,2,3,4,5,6,7 | Registers and Report | Community Services
|  |  | MTD4 | N/A | B2B_3 | To transform the municipality into a performance driven institution | Signing of annual performance agreements for Senior Managers | Number of Performance Agreements Signed | 1 | 1 | 1 | 1 | 1 | Achieved | N/A | N/A | N/A | N/A | Not applicable in Q2 | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | N/A | Institutional | Copy of signed agreement | Community Services
|  |  | MIDT8 | N/A | B2B-5 | To ensure that services provided to the Municipality by service providers is of high quality | Assess and Report on Service Providers Performance | Number of Bi-annual Reports Presented on the assessment of service providers | 2 | 4 | 2 | 1 | 1 | Achieved | N/A | N/A | N/A | N/A | Not applicable in Q2 | N/A | N/A | 1 | 1 | Achieved | 1 | N/A | N/A | Institutional | Reports on Service provider performance | Community Services
|  |  | MIDT10 | EXP-COMM | B2B-5 | To provide youth skills development programme | Skills development and training for out of school youth | Number of youth trained in Driving, ICT, job preparedness and construction related fields | 100 | 21 | 60 | Training plan approval by portfolio committee and Council | Training plan not approved by the Portfolio Committee and Council | Not Achieved | The training plan was not concluded in Q1 due to Covid 19 regulation | The target will be implemented by Q2 - 31 March 2021 | N/A | N/A | Not applicable in Q2 | N/A | N/A | Training plan approval by portfolio committee and Council | Training plan not approved by the Portfolio Committee and Council | Not Achieved | 30 | 30 | 885000 | Institutional | Training registers or certificates and invoices or proof of payment, committee minutes and council minutes register | Community Services
NKPA: LOCAL ECONOMIC DEVELOPMENT
KEY PERFORMANCE AREA: LOCAL ECONOMIC DEVELOPMENT | OUTPUT 3: IMPLEMENTATION OF THE COMMUNITY WORKS PROGRAMME | OUTCOME 4: DECENT EMPLOYMENT THROUGH INCLUSIVE GROWTH | LED1-1 | LED 20 | B2B-1 | To create a conducive environment for Local Economic and Rural Development | Monitor and report on the performance of rural development projects | Number of Agricultural Projects Supported through the LED Office | 7 additional per annum | 7 | 7 | Call for 7 additional projects to be supported and Progress report to portfolio committee and Council on 7 projects from 2020/21 | 7 projects supported for seedlings (for seedlings) | Achieved | N/A | N/A | N/A | N/A | Not applicable in Q2 | N/A | N/A | Call for 7 additional projects to be supported and Progress report to portfolio committee and Council on 7 projects from 2020/21 | 7 projects supported for seedlings (for seedlings) | Achieved | N/A | 7 | 150000 | Ward 1,2,3,4,5,6,7 | List of projects, Report and portfolio minutes or Council resolution | Community Services
|  |  | LED1-2 |  | B2B-1 |  |  | Number of reports on community assistance with livestock management | 2 | New | 2 | 1 - report on community assistance with livestock management | No Report for Community assistance with livestock management | Not Achieved | The programme has been on hold due to Lockdown regulations hence the delays in reporting. | 1 - report on community assistance with livestock management will be compiled by Q2 - 31 March 2021 | 1 | 2 | Achieved | N/A | N/A | 2 | 2 | Achieved | N/A | N/A |  | All wards represented | Report and portfolio report | Community Services
|  |  | LED1-3 |  | B2B-1 |  |  | Dates of events implemented to support agricultural projects | Quarterly events | New | 30 September 2020, 31 December 2020, 31 March 2021, 30 June 2021 | 2020/09/30 - Training of Coops | 2020-08-20 | Achieved | Training on Coops constitution and legislation | N/A | 2020/12/31 - Farmers Market event | Farmers market was not achieved | Not Achieved | Due to lockdown effects, the farmers market was postponed. | The market will be held by June 2021 | 2020/12/31 - Farmers Market event | Farmers market was not achieved | Not Achieved | 2021/03/31 - Farmers Gardens Competitions | 30 June 2021 - Farmers Market event |  | Ward 1,2,3,4,5,6,7 | Photos and report | Community Services
|  |  | LED1-4 | N/A | B2B-1 |  |  | Number of quarterly progress reports on LED projects submitted to the Admin and Community Services Portfolio | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Progress reports and Portfolio Minutes | Community Services
|  |  | LED1-5 | LED22 | B2B-1 |  | Coordinate Meetings for LED Forum | Number of forum meetings held | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 2 | Achieved | N/A | N/A | 2 | 3 | Achieved | 1 | 1 | N/A | Institutional | Minutes and attendance registers | Community Services
|  |  | LED2-1 | LED 19 | B2B-1 | To Promote emerging Businesses | SMME & Cooperatives support and training programme implemented | Number of SMME and Cooperatives trainings coordinated | 6 per annum | 2 | 6 | Training programme developed and submitted to Portfolio Committee | 1 | Achieved | N/A | N/A | 2 - Essential Business Documents and Essential Institutional Arrangements | 3 | Achieved | N/A | N/A | 2 - Essential Business Documents and Essential Institutional Arrangements | 4 | Achieved | 2 - Businesses in Cleaning services; Goods and Products Sourcing | 2 - Businesses in Construction ; Businesses in Hospitality | 152000 | Ward 1,2,3,4,5,6,7 | Correspondence, Training registers and/ or certificates | Community Services
|  |  | LED2-2 | LED 27 |  |  | To coordinate and host Mkhamba Fair Business EXPO | Date of Annual Mkhamba Fair | 31 May Annually | 2020-06-30 | 2021-05-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-05-31 | 300000 | Institutional (open to all wards) | Exhibitor's register and pictures | Community Services
|  |  | LED3-1a | LED006 | MK2 | To promote the rights of designated groups | Youth Programmes implemented | Date of Career Expo Exhibitions for in and out of school youth | End of quarter 3 | 2020-06-30 | 2021-02-28 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | 2021-02-28 | N/A | 130000 | Ward 1,2,3,4,5,6,7 | Registers, photos, reports | Corporate Services
|  |  | LED3-1b | LED008.2 | B2B-1 |  |  | Date of Matric Exams Prayer Day | End of quarter 1 | 2019-09-30 | 2020-09-30 | 2020-09-30 | 09-10 September 2020 | Achieved | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-09-30 | 09-10 September 2020 | Achieved | N/A | N/A | 125000 | Ward 1,2,3,4,5,6,7 | Registers, photos, reports | Community Services
|  |  | LED3-1c | LED008.1 | B2B-1 |  |  | Dates of Mkhambathini Achievement Awards programme | January and June annually | January and June | 31 January 2021 and 30 June 2021 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | 2021/01/31 (Schools) | 30 June 2021 (Community Awards) | 450000 | Ward 1,2,3,4,5,6,7 | Registers, photos, reports | Community Services
|  |  | LED3-2a | LED007.1 | B2B-1 |  | Coordinate Youth Council Activities | Number of Bi Annual youth Council Meetings held | 4 | 3 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | 1 | 1 | 200000 | Ward 1,2,3,4,5,6,7 | Minutes and attendance registers | Community Services
|  |  | LED3-2b |  | B2B-1 |  |  | Number of reports on youth Council activities submitted to Council | 4 | New | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | 1 | 1 |  | Ward 1,2,3,4,5,6,7 | Report and portfolio minutes | Community Services
|  |  | LED3-3 | LED0092 | B2B-1 |  | Coordinate establishment of Mkhambathini Special Programmes Forum | Date of Special Programmes Committee Launch | 2020-03-31 | New | 2021-03-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | 2021-03-31 | N/A | 55000 | Institutional, includes all wards | List of Committee Members and report to portfolio | Community Services
|  |  | LED3-4 | LED 10.3 | B2B-1 |  | Coordinate gender based activities | Number of Activities | 3 | New | 3 | 2 (Men's month and Women's day) | 1 | Not Achieved | Only 1 activity was done due to Covid restrictions | More activities will be done in Q2 | 1 (16 days of no violence against women and children) | 1 | Achieved | N/A | N/A | 2 (Men's month and Women's day) | 1 | Not Achieved | Report to portfolio Committee | N/A | 120000 | Ward 1,2,3,4,5,6,7 | Registers, pictures and report to committee | Community Services
|  |  | LED3-5 | LED009 | B2B-1 |  | Coordinate and host Senior Citizens event | Date of annual Christmas celebration | 31 December Annually | 2019-12-31 | 2020-12-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | 2020-12-10 | Achieved | N/A | N/A | 2020-12-31 | 2020-12-10 | Achieved | N/A | N/A | 415000 | Ward 1,2,3,4,5,6,7 | Report, Registers and photos | Community Services
|  |  | LED3-6 | N/A | B2B-1 |  | Coordinate meetings for people living with Disability | Number of meetings held for people living with disabilities | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | Meetings for disability was not achieved | Not Achieved | The forum Meeting did not convene due to unavailability of members | Meetings to resume in Q3, by 31 March 2021 | 2 | 1 Meeting for disability was not achieved | Not Achieved | 1 | 1 | N/A | Institutional | Minutes and attendance registers | Community Services
|  |  | LED3-7 | LED10.1 | B2B-1 |  | Coordinate programmes for people living with Disability | Date of awareness campaigns for people living with disabilities | Quarter 2 Annually | 2019-09-30 | 2020-11-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-11-30 | 18 and 19 November 2020 | Achieved | N/A | N/A | 2020-11-30 | 18 and 19 November 2020 | Achieved | N/A | N/A | 100000 | Ward 1,2,3,4,5,6,7 | Photos/ registers and close out report | Community Services
|  |  | LED3-7a | LED 10 | B2B-1 |  |  | Date of Annual disability celebration coordinated | 31 December Annually | 2019-12-31 | 2020-12-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | 2020-11-27 | Achieved | N/A | N/A | 2020-12-31 | 2020-11-27 | Achieved | N/A | N/A | 230000 | Ward 1,2,3,4,5,6,7 | Photos/ registers and close out report | Community Services
|  |  | LED3-7b | N/A | B2B-1 |  |  | Date of Local Disability games | Quarter 2 Annually | 2019-01-31 | 2020-12-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-12-31 | Games was not held | Not Achieved | Due to COVID 19, the Disbility games were postponed | These will resume after Covid19 regulations and levels have been lifted. | 2020-12-31 | Games was not held | Not Achieved | N/A | N/A | N/A | Institutional | Report and portfolio resolution | Community Services
|  |  | LED4-1a | LED11 | B2B-1 | To Promote Sports and Recreation | Coordinate participation in the Golden games by senior citizens of Mkhambathini Municipality | Date of Local golden games selections for 2020/2021 | 30 June annually | 2019-06-01 | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-06-30 | 80000 | Ward 1,2,3,4,5,6,7 | Registers and close out reports | Community Services
|  |  | LED4-1b | LED 11.3 and LED 11.4 | B2B-1 |  |  | Number of District and provincial golden games selection for 2020/2021 reports to portfolio committee | 2 | New | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | Report was not sent to portfolio committee | Not Achieved | Due to COVID 19, the dialogues were postponed | These will resume after Covid19 regulations and levels have been lifted. | 1 | Report was not sent to portfolio committee | Not Achieved | N/A | 1 | 185000 | Institutional | report and portfolio minutes | Community Services
|  |  | LED5-1 | LED009.1 | B2B-1 | To create awareness and a conducive environment to promote healthy lifestyles | Coordinate platforms for senior citizens engagements and dialogues | Number of Senior Citizens Workshops | 7 - one per ward | New | 7 | 1 | Senior citizen workshop Not Achieved | Not Achieved | Due to COVID 19, the dialogues were postponed | These will resume after Covid19 | 2 | Senior citizev workshop not achieved | Not Achieved | Due to COVID 19, the dialogues were postponed | These will resume after Covid19 regulations and levels have been lifted. | 2 | Senior citizev workshop not achieved | Not Achieved | 2 | 2 | 100000 | Ward 1,2,3,4,5,6,7 | Registers and report | Community Services
|  |  | LED5-2 | LED16 | B2B-1 |  | Coordinate and hold Local Aids Council Meetings | Number of local Aids Council meetings Coordinated | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | 15000 | Institutional | Registers and minutes | Community Services
|  |  | LED5-3 | LED15.2 | B2B-1 |  | To coordinate health awareness campaigns | Number of Bi-Annual on health awareness campaigns | 2 | 2 | 2 | N/A | 2 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 3 | Achieved | N/A | 1 | 123000 | Institutional | Correspondence and close out reports | Community Services
|  |  | LED5-4 |  | B2B-1 |  | Coordinate and hold a life skills programmes aimed at reducing teenage pregnancy, substance abuse and HIV/AIDS infections amongst youth | Number of iKusasalakho life skills programme workshops | 4 | 2 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | Workshop was not achieved | Not Achieved | Due to lockdown restrictions, work in schools was put on hold until it is deemed safe. | Workshops to resume after COVID19 regualtions and levels have been lifted | 2 | 1 | Not Achieved | 1 | 1 |  | Ward 1,2,3,4,5,6,7 | Registers and report | Community Services
|  |  | LED5-5 | LED17 | B2B-1 |  | To develop and submit the HIV Strategy to Council for approval | Date of strategy submission for approval by Council | 2020-03-31 | 2019-06-30 | 2020-08-31 | 2020-08-31 | HIV Strategy not tabled to Council for approval | Not Achieved | The strategy is still work in progress (Draft) | The KPI will be finalised by 30 March 2021 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | The strategy is still work in progress (Draft) and will be finalised by end of Q3 | The KPI will be finalised by 31 March 2020 | 2020-08-31 | HIV Strategy not tabled to Council for approval | Not Achieved | N/A | N/A | 105000 | Institutional | HIV/AIDS Strategy and Council Resolution | Community Services
|  |  | LED6 | LED 27.1 | B2B-1 | To promote tourism within the municipal area | To coordinate tourism promotion activities | Date of tourism brochure approval by Council | 2020-06-30 | New | 2021-05-31 | Project Steering Committee | Project steering Committee Not Achieved | Not Achieved | The brochure processes were put on hold as stakeholder engagement was not possible during lockdown | The processes will be done by 30 June 2021 | Appointment of brochure development | Appointment of brochure development Not Achieved | Not Achieved | The brochure processes were put on hold as stakeholde engaement was not possible during lockdown | The processes will be done by 31 June 2021 | Project Steering Committee | Project steering Committee Not Achieved | Not Achieved | Final Draft | 2021-05-31 | 180000 | Institutional | Brochure and Council resolution | Community Services
|  |  | LED7-1 | LED 28 | B2B-1 | To promote Arts and Culture Activities | Coordinate Reed Dance Activities | Date of reed dance activation and Life skills workshop for maidens | 30 June annually | New | 2021-06-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | Planning meeting with the Matrons | 2021-06-30 | 110000 | Ward 1,2 and 7 | Attendance Registers and photos | Community Services
|  |  | LED7-3 | LED38 and LED 29 |  |  | Coordinate Arts and Culture Activities | Dates of Arts and Culture Festival events | Quarterly dates | New | Quarterly dates , 31-Aug-20, 31-Dec-20, 31-Mar-21, 30-Jun-21 | 31 August 2020 - Activation Event | Arts and Culture Event Not Achieved | Not Achieved | Due to COVID 19, the events were postponed | These events will resume by Q4 30 June 2021 | 31 December 2020 - Mkhambathini Indlamu Festival | 14, 15, 22 and 29 November 2020 and 05, 06 and 12 December 2020 | Achieved | N/A | N/A | 31 December 2020 - Mkhambathini Indlamu Festival | 14, 15, 22 and 29 November 2020 and 05, 06 and 12 December 2020 | Achieved | 13 March 2021 - Mkhambathini Iscathamiya Festival | 30 June 2021 - Mkhambathini Gospel Festival | 550600 | Institutional | Close out report and photos | Community Services
|  |  | LED7-4 | LED29 |  |  |  | Dates of poetry development events | Quarterly dates | 2019-10-01 | Quarterly dates, 31-Aug-20,31- Dec-20, 31-Mar-21, 30- Jun-21 | 31 August 2020 - Poetry Development workshop | Poetry Development events Not Achieved | Not Achieved | Due to COVID 19, the events were postponed | These events will resume by Q4 30 June 2021 | 31 December 2020 - Mkhambathini Poetry Session | Poetry Event was Not Achieved | Not Achieved | Poetry develoment events were delayed due to the delay in execution of the Arts Festival Cometitions | Event to be conducted before30 June 2021 | 31 August 2020 - Poetry Development workshop | Poetry Development events Not Achieved | Not Achieved | 31 March 2021 - Poetry Festival | 30 June 2021 - Mkhambathini Poetry Session | 550600 | Ward 1,2,3,4,5,6,7 | Close out report and photos | Community Services
|  |  | LED7-5 |  |  |  | Coordinate Artist Development and Support activities | Number of activities per quarter | 4 | New | 4 | 1 | Artist development and support activities Not Achieved | Not Achieved | Due to COVID 19, the activities were postponed | These events will resume by Q4 30 June 2021 | 1 | Artist activities not achieved | Not Achieved | Artist develoment workshops were delayed due to the delay in execution of the Arts Festival Cometitions | Activities to be conducted before 30 June 2021 | 1 | Artist development and support activities Not Achieved | Not Achieved | 1 | 1 |  | Ward 1,2,3,4,5,6,7 | Registers or correspondence | Community Services
|  |  | LED7-6 | LED31 |  |  | Coordinate crafters development programme through training/ workshops | Number of crafters workshops/ training per annum | 2 | 1 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | 1 | 100000 | Ward 1,2,3,4,5,6,7 | Attendance Register/ Photos | Community Services
|  |  | LED9-1 | N/A | B2B-1 | To ensure effective implementation of Operation Sukuma Sakhe Programmes | Ensure functional OSS Task team (LTT) | Number of quarterly OSS Local Task Team Meetings | 4 | 4 | 4 | 1 | 2 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 3 | Achieved | 1 | 1 | N/A | Institutional | Minutes and attendance registers | Community Services
|  |  | LED9-2 | LED33 and LED37 | B2B-1 |  | Coordinate Operation Sukuma Sakhe Outreach Programmes | Date of Mandela day event | 31 July annually | 2019-07-18 | 2020-07-31 | 2020-07-31 | 13-18 July 2020 (PSW Activities) | Achieved | N/A | Registers on 9-3 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 2020-07-31 | 13-18 July 2020 (PSW Activities) | Achieved | N/A | N/A | 200000 | Institutional | Report and photos | Community Services
|  |  | LED9-3 |  | B2B-1 |  |  | Number of Operation MBO Activities | 7 | 1 | 7 | 1 | 3 | Achieved | N/A | See report and photos on LED9-2 | 2 | Operation MBO activities not achieved | Not Achieved | All Operation MBO activities were conducted as part of the PSW in Q1 | Operation MBO activities will resume after lockdown regualtions and levels have been lifted | 3 | 3 | Achieved | 2 | 2 |  | Ward 1,2,3,4,5,6,7 | Report and registers | Community Services
NKPA: FINANCIAL VIABILITY AND MANAGEMENT
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN3 | N/A | B2B_4 | To ensure effective and efficient supply chain management system | Develop the Departmental Procurement Plan to ensure timous procurement of required goods and services | Date of Submittion of procurement plan inputs to Finance | 30 April annually | New | 2021-04-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-04-30 | N/A | Institutional | Acknowledged from finance | Community Services
|  |  | Fin10-2b | FV0303 | B2B_4 | To ensure effective and efficient grants management | Spend 100% of the EPWP allocation by End of June 2019 | Quarterly Percentage reports spent on EPWP allocation (accumulative) | 100% | 100% | 100% | 25% | 53% | Achieved | N/A | Evidence on Fin 10-2b | 50% | 142% | Achieved | N/A | N/A | 50% | 142% | Achieved | 75% | 100% | R2m | Institutional | Reports submitted to Public Works | Community Services
|  |  | FIN10-2c |  | B2B_4 |  | Prepare and submit financial reports on EPWP allocation spending | Number of financial reports on % Spent on EPWP allocation submitted to Public Works | 12 | 12 | 12 | 3 | 3 | Achieved | N/A | N/A | 3 | 3 | Achieved | N/A | N/A | 3 | 3 | Achieved | 3 | 3 |  | Institutional | Report and proof of submission | Community Services
|  |  | FIN6-4 | N/A | B2B_4 | To ensure revenue enhancement | Revenue generated Through learners licensing | Amount of revenue Generated Through learners and Driver's licensing | R1.4M | R2.5M | R1.4M | 350000 | 751095.61 | Achieved | N/A | N/A | 350000 | 922486.88 | Achieved | N/A | N/A | 700000 | 1673583 | Achieved | 350000 | 350000 | N/A | Institutional | Finance system generated reports and correspondence from the billing office | Community Services
|  |  | FIN6-5 | N/A | B2B_4 |  | Revenue generated Through Motor Licensing | Amount of revenue Generated Through Motor Licensing | R1.2M | R1.2M | R1.2M | 300000 | 477467.36 | Achieved | N/A | N/A | 300000 | 906032.94 | Achieved | N/A | N/A | 600000 | 1383500 | Achieved | 300000 | 300000 | N/A | Institutional |  | Community Services
|  |  | FIN6-6 | N/A | B2B_4 |  | Prepare and submit reports Revenue generated through Learners, Drivers and Motor Licensing Licensing | Number of quarterly reports on learners licensing revenue generated submitted to finance portfolio committee | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Reports and portfolio minutes | Community Services
NKPA: GOOD GOVERNANCE
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1-3 | N/A | B2B_3 | To implement and maintain effective enterprise risk management system | Functional Risk Management through risk committee meetings | Number of quarterly risk management meetings held | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Risk register and minutes | Community Services
|  |  | GG4-1 | N/A | B2B_3 | To transform the municipality into a performance driven institution | Quarterly Performance Reports on achieved and not achieved targets submitted to PMS Unit | Number of quartely Performance Reports Submitted to PMS Unit | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Quarterly PMS Report and Submission register | Community Services
|  |  | GG9-1a | N/A | B2B_3 | To participate in the uMgungundlovu Economic Development Agency | To coordinate quarterly meetings with uMgungundlovu Economic Development Agency | Number of meetings held in quarterly | 2 | 3 | 4 | 1 (Deliberation on Mkhambathini Vision 2030) | 1 | Achieved | N/A | N/A | 1 (IGR Meeting regarding Vision 2030) | 2 | Achieved | N/A | N/A | 2 | 3 | Achieved | 1 (Transnet) | 1 (UMEDA) | N/A | Institutional | Registers | Community Services
|  |  | GG9-1b |  |  |  | Submit two progress reports to Portfolio Committee (after the planned bi-annual meetings) | Number of reports submitted to portfolio committee | 2 | New | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | 1 |  |  | Report and portfolio committee minutes | Community Services
NKPA: CROSS CUTTING
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC4-1 | LED 003 | B2B_2 | To ensure a functional Disaster Management Unit | Disaster Management Plan Developed and approved | Date of Disaster Management Plan Approved by Council | 2021-06-30 | N/A | 2021-05-31 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Consolidation of collected data and draft report to portfolio committee | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | Consolidation of collected data and draft report to portfolio committee | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | 2021-05-31 | 150000 | Institutional for All Wards | Council resolution and Disaster Management plan | Community Services
|  |  | CC4-2 | N/A | B2B_2 |  | Disaster Management Advisory Forum | Number. Of quarterly Disaster Management Advisory Forum meetings | 4 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | N/A | Institutional | Attendance registers and/or minutes | Community Services
|  |  | CC4-3b | N/A | B2B_2 |  | Provide Disaster Relief Support to families that have reported disaster incidents | Number of quarterly reports on Disaster relief support to families submitted to portfolio committee | 4 | N/A | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | 80000 | Institutional | Report and Portfolio Minutes | Community Services
|  |  | CC4-4 | LED 005 | B2B_2 |  | Disaster Management Awareness Campaigns | Number of quarterly Disaster Management Awareness campaigns | 4 | 2 | 4 | 1 | 1 | Achieved | N/A | N/A | 1 | 1 | Achieved | N/A | N/A | 2 | 2 | Achieved | 1 | 1 | 60000 | Institutional | Registers and correspondence | Community Services
|  |  | CC4-5 |  | B2B_3 |  |  | Number of Workshops for ward based structures on Disaster Management by the end of Quarter 3 | 7 | New | 7 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 4 (Ward 1, 2,3, 5) | Workshop was not achieved | Not Achieved | The workshops could not be convened due to lockdown regulations and activities (awareness raising campaigns) | Workshops will resume after lockdown | 4 (Ward 1, 2,3, 5) | Workshop was not achieved | Not Achieved | 3 (Ward 4, 6 and 7) | N/A |  | Ward based (W1-7) | Registers and reports | Community Services
|  |  | CC5-1 | N/A | B2B_2 | To enhance public safety control mechanisims | Review of Seasonal contigency plans for Mkhambathini Municipality | Dates of plans approval | Seasonal | Seasonal | Seasonal 30-12-20, 30-Jun-21 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 30 December 2020 (Summer plan) | 30 December 2020 (Summer plan) | Achieved | N/A | N/A | 30 December 2020 (Summer plan) | 30 December 2020 (Summer plan) | Achieved | N/A | 30 June 2021 (Winter Plan) | N/A | Institutional for wards | Safety plan and Council Resolution | Community Services
|  |  | CC5-2 |  | B2B_2 |  | Establishment of the Mkhambathini Animal Pound | Number of progress reports submitted to portfolio committee | 2 | 1 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 (Site identification) | Progress report not achieved | Not Achieved | Target to be removed | Target to be removed in the MidTerm by 30 January 2021 | 1 (Site identification) | Progress report not achieved | Not Achieved | N/A | 1 (Progress report) | N/A | Institutional | Report to Portfolio Committee | Community Services
|  |  | CC5-3 |  | B2B_2 |  | Establishment of the the Mkhambathini Municipality's Traffic Inspectorate | Quarterly progress reports submitted to portfolio committee | 2 | 1 | 2 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 1 | Progres report not achieved | Not Achieved | This is was not done as the process was halted by lockdown | Reports to be sent once the process resumes by Q4 30 June 2021 | 1 | Progres report not achieved | Not Achieved | 1 (Progress report) | N/A | N/A | Institutional | Report and Portfolio Minutes | Community Services
[13 empty] | 73.17% | 63.04%
[13 empty] | 26.83% | 36.96%

## Technical Serv
ORGANISATIONAL SCORECARD FOR 2020/2021 | [31 empty] | #VALUE!
TECHNICAL SERVICES DEPARTMENT
SDBIP MID TERM JANUARY ADJUSTMENT 2020/ 2021
ALIGNMENT WITH NATIONAL POLICY FRAMEWORK |  |  | IDP, BUDGET AND B2B REF NUMBERS (ALIGNMENT) |  |  | STRATEGIC OBJECTIVE | KEY PERFORMANCE INDICATORS | DETAILED PERFORMANCE MEASURE | DEMAND | BASELINE | ANNUAL TARGET | QUARTER 1 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | QUARTER 2 |  | ACHIEVED / NOT ACHIEVED | REASON FOR VARIANCE | CORRECTIVE ACTION | MIDTERM |  |  | QUARTER 3 | QUARTER 4 | BUDGET | WARD INFORMATION | Means of Verification (POE) | RESPONSIBLE DEPARTMENT | REFERENCE
|  |  | IDP REF NO. | MSCOA REF NO | B2B REF N0. |  |  |  |  | 2019/2020 | 2020/2021 | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL |  |  |  | TARGET | ACTUAL | ACHIEVED / NOT ACHIEVED | TARGET | TARGET
NKPA: BASIC SERVICE DELIVERY
|  |  | BSD1-1 | TBC | B2B_2 | To ensure the intergrated electrification development project within the Municipality | Ward 2 Electrification | Number of household electrified but not energised (accummulative) | 195 | New | 140 | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | N/A | N/A | Not for the period under review | N/A | 140 | 5000000 | Institutional | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-1 | TBC | B2B_2 | To ensure the provision, upgrade and construction of infrastructure and services that enhance socio economic development within the municipality | Manzamnyama Hall Ward 2 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 75% | 92% | ACHIEVED | N/A | N/A | 100% | 100% | ACHIEVED | N/A | N/A | 100% | 100% | ACHIEVED | N/A | N/A | 2800000 | Ward 2 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-2 | TBC | B2B_2 |  | Qedazulu Access Road Ward 5 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 20% | 95% | ACHIEVED | N/A | N/A | 80% | 100% | ACHIEVED | N/A | N/A | 100% | 100% | ACHIEVED | 100% | N/A | 8033000 | Ward 5 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-3 | TBC | B2B_2 |  | Mgwahumbe Gravel Road Ward 04 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 18% | ACHIEVED | N/A | N/A | 15% | 100% | ACHIEVED | N/A | N/A | 100% | 100% | ACHIEVED | 75% | 100% | 3277883.25 | Ward 4 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-4 | TBC | B2B_2 |  | Kwenzokuhle Community Hall Ward 06 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED | Projects were advertised and cancelled upon confirmation form COGTA that funds are no longer available | Target will be adjusted during adjustment period | 15% | 0% | NOT ACHIEVED | Project will be implemented on Multi-year 2020/21 and 2021/202 Financial Year, and contractor has been appointed. | Target will be adjusted during adjustment period | 40% | 0% | NOT ACHIEVED | 75% | 100% | 7949797.58 | Ward 6 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-5 | TBC | B2B_2 |  | Ezinembeni Creche - Ward 1 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 75% | 97% | ACHIEVED | N/A | N/A | 100% | 0 | NOT ACHIEVED | Projects were advertised and cancelled upon confirmation form Gogta that funds are no longer available | Target will be adjusted during adjustment period |  |  |  | N/A | N/A | 3888104 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-6 | TBC | B2B_2 |  | Ezinembeni Creche - Ward 1 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 75% | 80% | ACHIEVED | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 100% | 100% | ACHIEVED | N/A | N/A | 3890351.01 | Ward 1 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-8 | TBC | B2B_2 |  | Okhalweni Creche - Ward 7 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 75% | 97% | ACHIEVED | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 100% | 100% | ACHIEVED | N/A | N/A | 3888104 | Ward 1 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-9 | TBC | B2B_2 | To ensure the provision, upgrade and construction of infrastructure and services that enhance socio economic development within the municipality | Ascent Road Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 95% | NOT ACHIEVED | Completion was delayed due to Rain in December, but construction is at 95% and he revised completion date is 29 January 2021 | Construction is almost completed and contractor is currently attending snag list | 100% | 95% | NOT ACHIEVED | N/A | N/A | 660732.5 | Ward 7 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-10 | TBC | B2B_3 |  | Victoria Road - Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | N/A | N/A | 1079476.25 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-10 | TBC | B2B_4 |  | Alfread Storm Drive -Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | N/A | N/A | 851115 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-11 | TBC | B2B_5 |  | Charlton Place = Resurfacing of road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | N/A | N/A | 896770 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-12 | TBC | B2B_6 |  | Leylands Place - Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | N/A | N/A | 2037943.75 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-13 | TBC | B2B_7 |  | Woodcircle Road - Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | N/A | N/A | 1655712.5 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD2-14 | TBC | B2B_8 |  | Oehley Road - Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | 100% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | N/A | N/A | 3070612.12 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD3-1 | TBC | B2B_9 | To ensure that the municipal infrastructure assets are maintained | Gcina Gravel Road - Resurfacing of the road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED | There were delays regarding compiling BOQ which took more what we have anticipated | Tender documents are completed, and BID specification has considered the documents and are currently on SCM processes. Service providers will be appointed in December 2020 and construction will resume in January 2021 | 15% | 100% | NOT ACHIEVED | N/A | N/A | 50% | 100% | NOT ACHIEVED | 75% | 100% | 1000000 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD3-2 | TBC | B2B_2 |  | Ophokweni Community Hall | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED |  |  | 15% | 0% | NOT ACHIEVED | All service provider we appointed in December and construction will resume in January 2021 | We will FastTrack the implementation by closely monitoring the contractors. | 40% | 0% | NOT ACHIEVED | 75% | 100% | 1000000 | Ward 1 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD3-4 | TBC | B2B_2 |  | Dukes Hall Ward 04 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED |  |  | 15% | 0% | NOT ACHIEVED |  |  | 40% | 0% | NOT ACHIEVED | 75% | 100% | 1000000 | Ward 2 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD3-5 | TBC | B2B_2 |  | Banqobile Gravel Road | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED |  |  | 15% | 0% | NOT ACHIEVED |  |  | 40% | 0% | NOT ACHIEVED | 75% | 100% | 1000000 | Ward 3 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD3-6 | TBC | B2B_2 |  | Ismont (Philisiwe Ntombifuthi) Crèche Ward 06 | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED |  |  | 15% | 0% | NOT ACHIEVED |  |  | 40% | 0% | NOT ACHIEVED | 75% | 100% | 1000000 | Ward 4 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
|  |  | BSD3-7 | TBC | B2B_2 |  | KwaNdaya Community Hall | Percentage of the total project progress per quarter (accummulative) | 100% | New | 100% | 10% | 0% | NOT ACHIEVED |  |  | 15% | 0% | NOT ACHIEVED |  |  | 40% | 0% | NOT ACHIEVED | 75% | 100% | 1000000 | Ward 5 | Quarterly Progress Reports, Portfolio Committee Minutes / Practical Completion Certificates | Technical Services
NKPA: MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT
KEY PERFORMANCE AREA: MUNICIPAL INSTITUTIONAL DEVELOPMENT AND TRANSFORMATION | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | MIDT8 | N/A | B2B-5 | To ensure that services provided to the Municipality by service providers is of high quality | Assess and Report on Service Providers Performance | Number of Bi-annual Reports Presented on the assessment of service providers | 2 | 2 | 2 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | 1 | N/A | N/A | Institutional | Reports on Service provider performance | Technical Services
|  |  | MTD4 | N/A | B2B_5 | To transform the municipality into a performance driven institution | Signing of annual performance agreements for Senior Managers | Number of Performance Agreements Signed | 1 | 1 | 1 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
KEY PERFORMANCE AREA: FINANCIAL VIABILITY AND MANAGEMENT | OUTPUT 1: IMPLEMENTATION A DIFFERENTIATED APPROACH TO MUNICPAL FINANCING, PLANNING AND SUPPORT | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | FIN3 | N/A | B2B_4 | To ensure effective and efficient supply chain management system | Develop the Departmental Procurement Plan to ensure timous procurement of required goods and services | Date of submission Procurement plan inputs to finance | N/A | New | 2021-04-30 | N/A | N/A | NOT FOR THE PERIOD UNDER REVIEW | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
|  |  | Fin10-4 | IL07048 | B2B_4 | To ensure effective and efficient grants management | Spend 100% of the MIG allocation by End of June 2021 | Percentage spent on MIG allocation (accumulative) | 100% | 100% | 100% | 25% | 53.4% | ACHIEVED | N/A | N/A | 50% | 72,5% | ACHIEVED | N/A | N/A | 50% | 72.5% | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
|  |  | FIN10-5 | N/A | B2B_4 |  | Prepare and submit financial reports on MIG allocation spending | Number of financial reports on % Spent on MIG allocation | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
|  |  | FIN10-7 | IL07028 | B2B_4 |  | Prepare and submit financial reports on INEP grant allocation spending | Number of financial reports on % Spent on INEP allocation | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
NKPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
KEY PERFORMANCE AREA: GOOD GOVERNANCE AND DEMOCRACY | OUTPUT 1: IMPLEMENT A DIFFERENTIATED APPROACH TO MUNICIPAL FINANCING; PLANNING AND SUPPORT OUTPUT 5: DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL | OUTCOME 9: A RESPONSIVE, ACCOUNTABLE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | GG1-3 | N/A | B2B_3 | To implement and maintain effective enterprise risk management system | Functional Risk Management through risk committee meetings | Number of quarterly risk management meetings held | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
|  |  | GG4-1 | N/A | B2B_3 | To transform the municipality into a performance driven institution | Quarterly Performance Reports on achieved and not achieved targets submitted to PMS Unit | Number of quartely Performance Reports Submitted to PMS Unit | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
NKPA: CROSS CUTTING
KEY PERFORMANCE AREA : CROSS CURRING ISSUES | OUTPUT 7: SINGLE WINDOW OF COORDINATION | LE, EFFECTIVE AND EFFICIENT LOCAL GOVERNMENT SYSTEM | CC2 | N/A | B2B_2 | To ensure spatial development in the entire area of Mkhambathini Municipality | Approval of Spluma application | Quarterly Reports on approval of SPLUMA applications to council | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
|  |  | CC3 | N/A | B2B_2 | To promote effective and efficient building control services | Building inspections | Number of quarterly portfolio report on building inspections | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services
|  |  | CC6 | N/A | B2B_2 | To ensure integrated housing development within the municipality | Coordinate and hold meetings with Developers and the Department of Human Settlement | Number of quarterly Housing Meetings Held with developers and Department of Human Settlement | 4 | 4 | 4 | 1 | 1 | ACHIEVED | N/A | N/A | N/A | N/A | Not for the period under review | N/A | N/A | 1 | 1 | ACHIEVED | N/A | N/A | N/A | Institutional | Copy of signed agreement | Technical Services

## Sheet1
| Office of MM | Corporate Services | Financial Services | Community Services | Technical Services | Total KPI's
Basic Services |  |  |  | 8 | 20 | 28
MIDT | 3 | 12 | 2 | 5 | 2 | 24
Financial Viablilty | 2 | 2 | 22 | 6 | 4 | 36
Good Governance | 20 | 5 | 3 | 4 | 2 | 34
LED |  |  | 1 | 35 |  | 36
Cross Cutting | 3 | 1 | 3 | 8 | 3 | 18
| 28 | 20 | 31 | 66 | 31 | 176